Work Plan:  Kids in the Woods, Junior Watershed Science Training Program

June 2013 – October 2014

| TASKS | DESCRIPTION | Work Period |
| --- | --- | --- |
| Task 1. | Initiation and Coordination |  |
| 1.1 | Team/Staff Meeting | June – July 2013 |
| 1.2 | Press releases, radio interviews, web update | June 2013 - May 2014 |
| 1.3 | Select temperature monitoring sites, including near schools | June - July 2013 |
| 1.4 | Algae monitoring strategy (UCB/HCDPH/NCRWQCB) | June - July 2013 |
| 1.5 | Preliminary organizing with local contact from each school | June - August 2013 |
| 1.6 | Acquire and calibrate automated temp probes | June 2013 |
| Task 2 | Summer 2013 Field Activities |  |
| 2.1 | Summer organizing for selection/training of HS students to assist w/ monitoring | June - July 2013 |
| 2.2 | HRC aquatic trend monitoring in four Van Duzen tributaries with ERRP and students | August 2013 |
| 2.3 | Place Hobotemps in Streams | June - July 2013 |
| 2.4 | Check water temperature gauges mid-summer | August 2013 |
| 2.5 | Retrieve water temperature probes | October 2013 |
| Task 3 | Data Analysis, GIS, Mapping, and Reporting |  |
| 3.1 | Download data, perform QA/QC, format/organize | October - November 2013 |
| 3.2 | GIS mapping of temperature, algae, and salmon data and photopoints | November 2013 - January 2014 |
| 3.3 | Analyze data, share with classrooms, posters, circulate draft report, revise, and complete | October 2013 - June 2014 |
| 3.4 | Network students on salmon counts | October 2013 - January 2014 |
| Task 4 | School Programs |  |
| 4.1 | Meet with staff at local schools | August - September 2013 |
| 4.2 | Establish school liaison and protocols for transporting students | August - September 2013 |
| 4.3 | Purchase curriculum materials and supplies for schools | July - September 2013 |
| 4.4 | Produce posters and maps for classrooms | July - September 2013 |
| 4.5 | Prep Elementary classes on salmon (salmon ID cards) | October - November 2013 |
| 4.6 | Develop Projects with Fortuna High School, Southern Trinity High School | July 2013 - June 2014 |
| Task 5 | Educational Field Activities |  |
| 5.1 | Hydesville, Bridgeville, Cuddeback : Field trips to Scotia Aquarium | October - December 2013 |
| 5.2 | Two-day workshops at each elementary school | September - November 2013 |
| 5.3 | Salmon spawning ground field trips | November 2013 - January 2014 |
| 5.4 | Monitoring at selected Sites (turbidity and flow) | September 2013 - June 2014 |
| 5.5 | Field trip (wildflowers, riparian, and geology) | March - April 2014 |
| 5.6 | Conduct educational field days at Grizzly Creek, Six Rivers National Forest | April - May 2014 |
| 5.7 | Involve students in Van Duzen River riparian restoration project | April - August 2014 |
| Task 6 | Ecology and Arts |  |
| 6.1 | River poetry in schools and in the field | September 2013 - June 2014 |
| 6.2 | Musical compositions by students | September 2013 - June 2014 |
| 6.3 | Watershed drawings, puppets, & sculptures | September 2013 - June 2014 |
| 6.4 | Video Projects by students | September 2013 - June 2014 |
| Task 7 | Outreach |  |
| 7.1 | PTA & School Board Meetings | September 2013 - June 2014 |
| 7.2 | Public Meeting (Carlotta Grange) | March - April 2014 |
| 7.3 | Press Releases | July 2013 - June 2014 |
| 7.4 | Web updates, maps, photos, student work, etc. | August 2013 - June 2014 |
| 7.5 | Water Day 2014 | March 2014 |
| Task 8 | Reports |  |
| 8.1 | Salmon migrations & spawning in Van Duzen | January - February 2014 |
| 8.2 | Water quality: temperature, algae, turbidity, and flow | January – July 2014 |
| 8.3 | Final Report | June – October 2014 |