# STATUS OF SCOPAC THPs

# AS OF

## February 17, 2006

[ 0]	THPs Approved (Friday 2/10/06 – Thursday 2/16/06)

None

[ 0]   THPs Potentially Available for Signature beginning on Friday 2/17/06 (if all required information is received and OR completed - if required)

None

[ 1]    THPs Processed Through 2nd Review Awaiting Close of the Public Comment Period

1-05-242 (LE Nanning)	Recommended for approval WITHOUT additional mitigation.  Public comment period to close on 2/23/06 (PHI begun on 1/18/06 and completed on 1/24/06).  Submitted as a HCP Option “A” THP utilizing the Lower Eel/Eel Delta Watershed Analysis Prescriptions.

Director’s Decision Date:  3/16/06

[ 2]  THPs with Special Circumstances Delaying Final Determination

1-04-220 (Horse 04)	Recommended for approval WITHOUT additional mitigation.  Public comment closed on 11/5/04 (PHI held on 10/6/04).  Non-concurrence filed by WQ on 10/26/04 (winter operations & 10 foot no cut buffer adjacent to Class III watercourse).  Non-concurrence filed by DPR on 10/25/04 (visual impact).  Final decision delayed pending resolution of non-concurrences and potential sale of portion of area containing old-growth redwood.  Received revision to plan deleting the 44 acres not included in the potential sale agreement on 10/14/05.  Total plan acreage reduced to 21 acres.  Submitted as an Option “C” THP utilizing the Lower Eel/Eel Delta Watershed Analysis prescriptions.

Director’s Decision Date:  2/28/06

1-05-123 (Mid Incline)*	Recommended for approval with additional mitigation (AM1).  Public comment closed on 10/28/05 (PHI begun on 7/12/05 and completed on 7/22/05).  Received RPF response to 2nd RT recommendations on 10/18/05.  WQ filed a non-concurrence (Class III protection issues) on 10/18/05.  Submitted as a HCP Option “A” utilizing the Freshwater Watershed Analysis Prescriptions.

Director’s Decision Date extended to allow time to resolve WQ non-concurrence

Director’s Decision Date:  2/28/06

[ 0] 	THPs Recommended for Approval at 2nd Review in Fortuna on 2/16/06

None

[ 0]	Recommended for Denial at 2nd Review in Fortuna

None

[ 2]	2nd Review Postponed

1-05-006 (City Dump)	Recommended for approval with additional mitigation.  Public comment period closed on 4/22/05 (PHI begun on 2/23/05 and completed on 3/3/05).  Received RPF response to 2nd RT recommendations on 4/8/05.  Plan taken back to 2nd review due to additional of new access road through landfill area.  2nd review scheduled for 1/12/06 postponed due to issues raised by WQ concerning use of road through landfill by loggings trucks and other related issues.  WQ feels their landfill use permit does not allow for roads to be used by log trucks.  Submitted as a regular THP by SCOPAC (timber owner) for the timberland owner, City Garbage Company of Eureka.   Option “C” THP.

Director’s Decision Date:  2/28/06

1-05-194 (Pitchfork)	PHI held on 10/11/05.  Received CDF PHI report on 10/14/05.  Received CGS PHI report on 10/18/05.  Received RPF response to CDF and CGS PHI reports on 11/7/05.  Received WQ PHI report on 11/9/05.  Received RPF response to WQ PHI recommendations on 11/10/05.  Received additional WQ PHI report on 1/26/06.  Received RPF response to additional WQ PHI report on 2/2/06.  2nd review scheduled for 11/17/05 postponed due to unresolved WQ Bear Creek issues..  Submitted as a HCP Option “A” THP utilizing the Lower Eel/Eel Delta Watershed Analysis Prescriptions.

[ 2]	THPs Awaiting Second Review, Pending Receipt of Information from SCOPAC, or Completion

Of Consultations

1-05-214 (Horse Hockey)	PHI held on 12/20, 21 and 28/05.  Received CGS PHI report on 1/9/06.  Received DPR PHI report on 1/9/06.  Received CDF PHI report on 1/10/06.  Received DFG PHI report on 1/12/06.  Received WQ PHI report on 1/26/06.  Need RPF response to PHI recommendations.  Submitted as a HCP Option “A” THP utilizing the Lower Eel/Eel Delta Watershed Analysis Prescriptions.

1-06-002 (VDT 06)	PHI held on 1/31/06.  Received CDF PHI report on 2/8/06.  Received CGS PHI report on 2/9/06.  Need RPF response to PHI recommendations.  Submitted as a HCP Option “A” THP utilizing the Van Duzen Watershed Analysis Prescriptions.

[ 5]	THPs That Need Agency reports or additional Agency Information Prior to 2nd Review

1-05-079 (Second Serving)**	PHI held on 11/9 & 10/05 and completed on 1/13/06.  Received CDF PHI report on 1/25/06.  Received CGS PHI report on 1/27/06.  Need WQ PHI report.  Submitted as a HCP Option “A” THP utilizing the Elk River/Salmon Creek Draft Watershed Analysis prescriptions.  Note: Prior to 2nd review, the THP must be revised to include the final, approved Elk River/Salmon Creek Watershed Analysis Prescriptions (approved on 11/16/05 – 8/12/05 version).

1-05-131 (Magnum Opus)**	PHI held on 11/1 and 2/05.  Received CGS PHI report on 11/8/05.  Received CDF PHI report on 11/10/05.  Need WQ PHI report.  Submitted as a HCP Option “A” THP utilizing the draft Elk River/Salmon Creek Watershed Analysis Prescriptions.   Note: Prior to 2nd review, the THP must be revised to include the final, approved Elk River/Salmon Creek Watershed Analysis Prescriptions (approved on 11/16/05 – 8/12/05 version).

1-05-248 (LE Kiler)	PHI held on 1/18/06.  Received CGS PHI report on 1/31/06.  Received WQ PHI report on 2/7/06.  Need CDF PHI report.  Submitted as a HCP Option “A” THP utilizing the Lower Eel/Eel Delta Watershed Analysis Prescriptions.

1-05-254 (Munson)	PHI held on 1/23/06.  Received ARCH PHI report on 1/30/06.  Received CGS PHI report on 2/2/06.  Received CDF PHI report on 2/10/06.  Need  WQ PHI report.  Submitted as a HCP Option “A” THP utilizing the Lower Eel/Eel Delta Watershed Analysis Prescriptions.

1-05-255 (LE Monument)	PHI held on 1/23/06.  Need CDF and CGS PHI reports.  Submitted as a HCP Option “A” THP utilizing the Lower Eel/Eel Delta Watershed Analysis Prescriptions.

[  5]  Plans In Early Stages of Review (prior to completion of PHI)

1-05-161 (John Doe)**	PHI held on 12/13 & 14/05.  PHI remains open pending resolution of CGS issue.  May require another field visit.  Pending resolution of CGS issue.  Need CDF, CGS and WQ PHI reports..  Submitted as a HCP Option “A” THP utilizing the draft Elk River/Salmon Creek Watershed Analysis Prescriptions.   Note: PHI can not be scheduled until the wildlife agencies approve the ERSC Watershed Analysis prescriptions (approved on 11/16/05 – 8/12/05 version).

1-05-233 (Corbett 06)	Filed on 12/15/05.  PHI scheduled for 2/7 and 8/06 postponed due to weather.  Pending rescheduling of PHI.  Submitted as a HCP Option “A” THP utilizing the Van Duzen Watershed Analysis Prescriptions.

1-05-237 (PC Road)	Filed on 12/22/05.  Pending scheduling of PHI.  Note – PHI may not be scheduled until final adaptive management language regarding harvesting on “Steep Hillslope” and “MWAC” areas by the wildlife agencies.  Submitted as a HCP Option “A” THP utilizing the Interim Watershed Prescriptions (Bear River).

1-05-243 (Poison Oak Eel)	Filed on 1/2/06.  Received on 12/19/05.  Returned 12/23/05 – NOI issue.  Resubmitted on 12/23/05.  Pending scheduling of PHI.  Note – PHI may not be scheduled until final adaptive management language regarding harvesting on “Steep Hillslope” and “MWAC” areas by the wildlife agencies.  Submitted as a HCP Option “A” THP utilizing the HCP Interim Prescriptions.

1-06-001 (Brush Up)	Filed on 1/13/06.  Pending scheduling of PHI.    Note – PHI may not be scheduled until final adaptive management language regarding harvesting on “Steep Hillslope” and “MWAC” areas by the wildlife agencies.  Submitted as a HCP Option “A” THP utilizing the HCP Interim Watershed Prescriptions.

[ 0]    THPs Returned

None

[ 0]	THP Major Amendments

None

SUMMARY

[  0]   THPs Approved (Friday 2/10/06 – Thursday 2/16/06)

[  0]	THPs Potentially Available for Signature beginning on Friday 2/17/06.

[  1]   THPs Processed Through 2nd Review Awaiting Close of the Public Comment Period

[  2]	THPs  with Special Circumstances Delaying Final Determination

[  0]	THPs Recommended for Approval at  2nd Review in Fortuna on 2/16/06.

[  0]	Recommended for Denial at 2nd Review

[  2]   2nd Review Postponed

[  2]  THPs Awaiting Second Review Pending Receipt of Information from SCOPAC and/or Completion

of  Consultations

[  5]	THPs That Need Agency reports or additional Agency Information Prior to 2nd Review

[  5]	Plans In Early Stages of Review (prior to completion of PHI)

[  0]	THPs Returned

[  0]	THP Major Amendments

SUMMARY OF REPORT ACTIVITY:

[  0]	THPs Approved  2/10/06 – 2/16/06

[  0]  	Major Amendments Approved 2/10/06 – 2/16/06

[17]	THPs Under Review as of 2/17/06

[  0]	Major Amendment Under Review as of 2/17/06

##### [17]   Total Plans/Amendments Under Review as of 2/17/06

-end-